## Read me
Business case
UC-01: Supplier delivery notes captured into the ERP without manual typing
FICTIONAL EXAMPLE. All names and figures are invented for illustration ("Northwind Aero Services").
How to use
1. Enter inputs on the 'Inputs' sheet (blue text on yellow = input). Everything else is a formula.
2. Enter the pessimistic and optimistic values of the three most uncertain inputs on 'Scenarios'.
3. Record the source and confidence of every input on 'Assumptions log'.
4. Read the results on 'Calculation'. 'Cash flow' shows the 36 months behind payback and NPV.
Counting rules
- A benefit counts only once. If the same saved hours or avoided errors appear in another use case, count them in one case only.
- Hours saved are not cash. They count as cash only if they are redeployed to valued work or a cost is avoided (overtime, temporary staff, a planned hire). The share is an explicit input; the rest is shown as 'not counted'.
- Benefits ramp up with adoption. Nothing starts at 100% on day one.
- Run costs are part of the case: licences, hosting, monitoring, support, retraining.
- Scenarios change only the three most uncertain inputs. All other inputs stay at their base value.
- Every input has a source or reasoning and a confidence level in the assumptions log.
- A negative scenario is a decision input, not a footnote. If the 3-year NPV is negative in any scenario, the case can only be approved with conditions: a review gate 3 months after go-live, and stop or rework if adoption or time saved fall to their pessimistic values.
Nothing in this workbook is protected. Results are recalculated when the file is opened.

## Inputs
Inputs
UC-01: Supplier delivery notes captured into the ERP without manual typing
FICTIONAL EXAMPLE. All names and figures are invented for illustration ("Northwind Aero Services").
Group | ID (defined name) | Input | Value | Unit
Process | volume_per_month | Transactions per month | 3000 | delivery notes / month
Process | minutes_before | Handling time per transaction today | 6 | minutes
Process | minutes_after | Handling time per transaction with the AI solution | 2 | minutes (base; see Scenarios)
Process | hourly_cost_eur | Fully loaded cost per hour | 70 | EUR / hour
Process | share_hours_redeployed | Share of saved hours redeployed or avoiding a cost | 50% | share (0-1) (base; see Scenarios)
Process | error_rate_before | Error rate today | 3% | share of transactions
Process | error_rate_after | Error rate with the AI solution | 1% | share of transactions
Process | cost_per_error_eur | Cost per error | 50 | EUR / error
Costs | licence_cost_per_year_eur | Licence cost per year | 18000 | EUR / year
Costs | build_days | Internal build effort | 60 | person-days
Costs | day_rate_eur | Internal day rate | 600 | EUR / day
Costs | other_one_off_eur | Other one-off costs | 15000 | EUR
Costs | run_cost_per_year_eur | Run cost per year | 12000 | EUR / year
Adoption and finance | adoption_initial | Adoption during the ramp-up | 50% | share of volume
Adoption and finance | ramp_months | Length of the ramp-up | 3 | months
Adoption and finance | adoption_steady | Adoption after the ramp-up | 80% | share of volume (base; see Scenarios)
Adoption and finance | discount_rate | Discount rate | 8% | per year

## Scenarios
Scenarios: the three most uncertain inputs
UC-01: Supplier delivery notes captured into the ERP without manual typing
FICTIONAL EXAMPLE. All names and figures are invented for illustration ("Northwind Aero Services").
ID | Input | Pessimistic | Base | Optimistic | Unit | Why it is uncertain
minutes_after | Handling time per transaction with the AI solution | 3 |  | 1.5 | minutes | Checking time depends on extraction quality across 400 supplier layouts.
share_hours_redeployed | Share of saved hours redeployed or avoiding a cost | 25% |  | 75% | share (0-1) | Depends on whether the claims backlog really absorbs the freed time.
adoption_steady | Adoption after the ramp-up | 60% |  | 90% | share of volume | Depends on how many suppliers send machine-readable PDFs.
Base values come from the Inputs sheet. Change them there.

## Calculation
Calculation
UC-01: Supplier delivery notes captured into the ERP without manual typing
FICTIONAL EXAMPLE. All names and figures are invented for illustration ("Northwind Aero Services").
Metric | How it is calculated | Pessimistic | Base | Optimistic
Effective inputs
Transactions per month | Inputs sheet (same in all scenarios)
Handling time per transaction today | Inputs sheet (same in all scenarios)
Handling time per transaction with the AI solution | Scenarios sheet
Fully loaded cost per hour | Inputs sheet (same in all scenarios)
Share of saved hours redeployed or avoiding a cost | Scenarios sheet
Error rate today | Inputs sheet (same in all scenarios)
Error rate with the AI solution | Inputs sheet (same in all scenarios)
Cost per error | Inputs sheet (same in all scenarios)
Licence cost per year | Inputs sheet (same in all scenarios)
Internal build effort | Inputs sheet (same in all scenarios)
Internal day rate | Inputs sheet (same in all scenarios)
Other one-off costs | Inputs sheet (same in all scenarios)
Run cost per year | Inputs sheet (same in all scenarios)
Adoption during the ramp-up | Inputs sheet (same in all scenarios)
Length of the ramp-up | Inputs sheet (same in all scenarios)
Adoption after the ramp-up | Scenarios sheet
Discount rate | Inputs sheet (same in all scenarios)
Results
Hours saved per month at full adoption | volume x (minutes before - after) / 60
of which counted as cash | hours saved x share redeployed
Cash value of redeployed hours per month | hours counted as cash x hourly cost
Errors avoided per month at full adoption | volume x (error rate before - after)
Value of errors avoided per month | errors avoided x cost per error
Monthly benefit at full adoption | cash value of hours + value of errors avoided
Annual benefit at steady adoption | 12 x monthly benefit x steady adoption
One-off cost (month 0) | build days x day rate + other one-off costs
Annual run cost | licence + run cost per year
Payback (months) | first month with cumulative net cash flow >= 0
3-year NPV | sum of monthly net cash flows discounted at (1 + rate)^(month / 12)
Total benefit over 3 years | sum of monthly benefits
Total cost over 3 years | one-off + monthly run costs
Simple ROI over 3 years | (total benefit - total cost) / total cost
Not counted: value of saved hours not redeployed, per year | for information only; not in NPV
Hours are counted as cash only for the redeployed share. See the counting rules on 'Read me'.

## Cash flow
Monthly cash flow (36 months)
UC-01: Supplier delivery notes captured into the ERP without manual typing
FICTIONAL EXAMPLE. All names and figures are invented for illustration ("Northwind Aero Services"). | Pessimistic | [6 empty] | Base | [6 empty] | Optimistic
Month | Adoption | Benefit | Cost | Net | Cumulative | Discounted net | Payback month | Adoption | Benefit | Cost | Net | Cumulative | Discounted net | Payback month | Adoption | Benefit | Cost | Net | Cumulative | Discounted net | Payback month
0
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36

## Assumptions log
Assumptions log
UC-01: Supplier delivery notes captured into the ERP without manual typing
FICTIONAL EXAMPLE. All names and figures are invented for illustration ("Northwind Aero Services").
ID | Input | Value (base) | Unit | Source or reasoning | Confidence | Scenario range
volume_per_month | Transactions per month |  | delivery notes / month | Goods-receipt log, 12-month average (fictional). | high
minutes_before | Handling time per transaction today |  | minutes | Time study on a sample of 50 notes (fictional). | medium
minutes_after | Handling time per transaction with the AI solution |  | minutes | Vendor demo on 30 sample notes; clerk checks and confirms each pre-filled receipt. | low | 3 / base / 1.5
hourly_cost_eur | Fully loaded cost per hour |  | EUR / hour | Controlling standard rate (fictional), including salary, social charges and overhead. | high
share_hours_redeployed | Share of saved hours redeployed or avoiding a cost |  | share (0-1) | Process owner plan to move time to the backlog of supplier claims; the rest is absorbed and not counted as cash. | low | 0.25 / base / 0.75
error_rate_before | Error rate today |  | share of transactions | Stock-count findings traced to keying errors (fictional). | medium
error_rate_after | Error rate with the AI solution |  | share of transactions | Remaining errors from low-confidence fields the clerk does not catch; estimate. | medium
cost_per_error_eur | Cost per error |  | EUR / error | Rework time plus stock correction, estimated by the process owner. | medium
licence_cost_per_year_eur | Licence cost per year |  | EUR / year | Indicative vendor quote for the document volume (fictional). | high
build_days | Internal build effort |  | person-days | IT estimate for interface, configuration, testing and key-user time. | medium
day_rate_eur | Internal day rate |  | EUR / day | Controlling internal rate (fictional). | high
other_one_off_eur | Other one-off costs |  | EUR | Training, change management and an external integration partner. | medium
run_cost_per_year_eur | Run cost per year |  | EUR / year | Hosting, monitoring, support and a monthly quality sample. | medium
adoption_initial | Adoption during the ramp-up |  | share of volume | Typical first-quarter adoption; only PDF notes from the largest suppliers at first. | medium
ramp_months | Length of the ramp-up |  | months | Roll-out plan. | medium
adoption_steady | Adoption after the ramp-up |  | share of volume | About 20% of notes are handwritten or unusual layouts and stay manual. | low | 0.6 / base / 0.9
discount_rate | Discount rate |  | per year | Finance standard rate for internal projects (fictional). | high